## Test Scenario
Test Scenario
Project Name: | REDIFF |  | Project Start Date: | 2025-11-16
Version Number: | V0.0.1 |  | Project End Date: | 2026-02-25
Author Name: | Pavan Kalyan L
Review Date | 2025-11-26 |  | Review Status | Yet to review
Module | Scenario ID | Scenario | Description | Reference ID
Account Creation | TC_001 | Rediff Account Creation | To validate the Rediff of the facebook account creation

## Test Case
Test Case
| Project Name: |  |  | Project Start Date:
| Version Number: |  |  | Estimate Project End Date:
| Author Name: |  |  | Test Execution Date
| Review Date |  |  | Review Status
Test Case ID | Test Case Description | Test Case Priority | Pre-Condition | Test Step | Test Data | Expected Result | Actual Result | Status | Defect Id | Attachments
TC_001 | To validate Rediff account creation functionality with valid inputs | 1 | Launch browser with url "www.rediff.com" and navigate to account creation page | 1. Enter name in the "Full name" filed | Pavan Kalyan L | The entered data should be displayed in the "Full name" field
|  |  |  | 2. Enter the rediff mail in the "Rediff Mail" filed | pavankalyanl@rediffmail.com | The entered data should be displayed in the "Rediff Mail" field
|  |  |  | 3. Enter password in the "Choose password" field | Kalyan@1318 | The entered data should be displayed in the "Choose password" field
|  |  |  | 4. Enter password in the "Retype password" field | Kalyan@1318 | The entered data should be displayed in the "Retypee password" field
|  |  |  | 5. Select Date of Birth | 2025-05-13 | The selected data should be displayed in the Date of Birth field
|  |  |  | 6. Select Gender | Male | The selected Gender should be displayed
|  |  |  | 7. Select a Country | India | The Selected Country should be displayed
|  |  |  | 8. Select a City | Chennai | The Selected City should be displayed
|  |  |  | 9. Enter the recovery mail in the "Recoverey Mail" filed | pavankalyanl1318@gmail.com | The entered data should be displayed in the "Recovery Mail" field
|  |  |  | 10. Click Click if you don't have an alternate ID below "Recoverey mail" Field | NA
|  |  |  | 11.Enter a mobile number in the "Mobile Number" field | 9345362981 | The entered data should be displayed in the "Mobile number " field
|  |  |  | 12. Enter the Capcha, text shown above in the "Enter Capcha" Field | NYBA | The entered data should be displayed in the "Enter Capcha" field
|  |  |  | 13. Click on "Create my account" button | NA | The news account created successfully
TC_002 | To validate Rediff account creation functionality withIn valid inputs | 1 | Launch browser with url "www.rediff.com" and navigate to account creation page | 1. Enter name in the "Full name" filed | Pavan Kalyan L | The entered data should be displayed in the "Full name" field
|  |  |  | 2. Enter the rediff mail in the "Rediff Mail" filed | pavankalyan@rediffmail.com | The entered data should be displayed in the "Rediff Mail" field
|  |  |  | 3. Enter password in the "Choose password" field | Kalyan@1318 | The entered data should be displayed in the "Choose password" field
|  |  |  | 4. Enter password in the "Retype password" field | Kalyan@1318 | The entered data should be displayed in the "Retypee password" field
|  |  |  | 5. Select Date of Birth | 2025-05-13 | The selected data should be displayed in the Date of Birth field
|  |  |  | 6. Select Gender | Male | The selected Gender should be displayed
|  |  |  | 7. Select a Country | India | The Selected Country should be displayed
|  |  |  | 8. Select a City | Chennai | The Selected City should be displayed
|  |  |  | 9. Enter the recovery mail in the "Recoverey Mail" filed | pavankalyanl1318@gmail.com | The entered data should be displayed in the "Recovery Mail" field
|  |  |  | 10. Click Click if you don't have an alternate ID below "Recoverey mail" Field | NA
|  |  |  | 11.Enter a mobile number in the "Mobile Number" field | 9345362981 | The entered data should be displayed in the "Mobile number " field
|  |  |  | 12. Enter the Capcha, text shown above in the "Enter Capcha" Field | NYBA | The entered data should be displayed in the "Enter Capcha" field
|  |  |  | 13. Click on "Create my account" button | NA | The error message "Sorry , that ID that you are looking for is taken
TC_003 | To validate the rediff account creation functionality with field level validation of First name field | 2 | Launch browser with url "www.rediff.com" and navigate to account creation page | Leave "Full name" fields as blank and move to next field |  | The error message "First name field is mandatory" should be displayed
|  |  |  | Enter the alphabet and numeric value in the "First name" field | kalyan1318 | The entered data should be displayed in the "First name" field
|  |  |  | Enter the name with special character in the "First name" field | Kalyan$#% | The error message "First name field should not contain special characters" should be displayed
|  |  |  | Enter the name with special character in the "First name" field | Pavan_Kalyan , Pavan.Kalyan | The entered data should be displayed in the "First name" field
TC_004 | To validate redifMail Account Creation functionality with field level validation of "RediffMail ID" field | 4 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | Pavan Kalyan L | The enterd data should be displayed in the "Full name" field | The enterd data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the mail with alphanumerc in the "RediffMail ID" field | PavanKalyanL | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Leave the "RediffMail Id" blsnk and move to the next field |  | The error message "The RediffMail Id field is manditatory" should be displayed | The error message "The RediffMail Id field is manditatory" is displayed | pass
|  |  |  | 4.Enter the mail with the special characters except("@",".","_") in the "Rediffmail Id" field | pavankalyan#@rediffmail.com | The error message "The RediffMail Id should not contain special characters" should be displayed | The error message "The RediffMail Id should not contain special characters" is displayed | pass
TC_005 | To validate RediffMail account creation functionality with field level validation of "Password" field | 5 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | Pavan Kalyan L | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | PavanKalyan1318 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Leave the "password" field blank and move to the next field | NA | The error message "Password field is mandatory" should be displayed | The error message "Password field is mandatory" is displayed | pass
|  |  |  | 4.Enter the password that contains minimum of 6 characters with one capital,numeric,special character in the "Password" field | Kalyan@1318 | The entered data should be displayed in the "password" field | The entered data is displayed in the "password" field | pass
|  |  |  | 5.Enter the password that consist of less than 6 characters in the "Password" field | Kal@13 | The error message "The Password must contain a minimum of 6 characters" should be displayed | The error message "The Password must contain a minimum of 6 characters" is displayed | pass
TC_006 | To validate the RediffMail Account creation functionality with the field level validation of "Retype Password" field | 6 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jay | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 13/05/2005 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.Select the CIty | Chennai | The entered data should be displayed in the "city" field | The entered data is displayed in the "city" field | pass
|  |  |  | 9.Enter the Recovery mail in the "Recovery email" field | man@gmail.com | The entered data should be displayed in the "Recovery mail" field | The entered data is displayed in the "Recovery mail" field | pass
|  |  |  | 10.select the "check box" |  | The blue color tick should de displayed in the "check box" field | The blue color tick should de displayed in the "check box" field | pass
|  |  |  | 11.Enter the mobile in the "Mobile Number'' field | 7010516617 | The entered data should be displayed in the"Monile Number" field | The entered data is displayed in the"Monile Number" field | pass
|  |  |  | 12.Enter the captcha in the "Captcha " field | NA | The entered data should be displayed in the " Captcha" field | The entered data is displayed in the " Captcha" field | pass
|  |  |  | 13.Click on the "Sign up" button | NA | The error message "The password field and the Retype password field must match" should be displayed | No error message is displayed | Fail
TC_007 | To validate RediffMail account creation functionality with field level validation of "Date of Birth" field | 7 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | Pavan Kalyan L | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | Pavankalyan1318@gmail.com | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | Kalyan@1318 | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | Kalyan@1318 | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.verify all dates all are displayed in the date dropdown | N/A | All the dates from 1 to 31 must be displayed | All the dates from 1 to 31 must be displayed | pass
|  |  |  | 6.verify all the months are displayed in the month dropdown field | N/A | All the months must be displayed in the month dropdown field | All the months must be displayed in the month dropdown field | pass
|  |  |  | 7.verify all the year are displayed in the dropdown field | N/A | All the year from 1905 to 2025 must be displayed | All the year from 1905 to 2025 must be displayed | pass
TC_008 | To validate RediffMail account creation functionality with field level validation of "Gender" field | 8 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jai | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.verify both the male and female are diplayed in the "Gender" field | Male | Both the male and female must be displayed in the dropdown field | Both the male and female must be displayed in the dropdown field | pass
TC_009 | To validate RediffMail account creation functionality with field level validation of "l Live in" field | 9 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jai | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Verify all the countries are displayed in the "I Live In" dropdown field | NA | All the countries are displayed in the "I Live In" dropdown field | All the countries are displayed in the "I Live In" dropdown field | pass
TC_010 | To validate RediffMail account creation functionality with field level validation of "City" field | 10 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jai | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.verify all the city are displayed in the "city" dropdown field | NA | All the cities are visible in the "city" dropdown field | All the cities are visible in the "city" dropdown field | pass
TC_011 | To validate RediffMail account creation functionality with field level validation of "My Recovery Email" field | 11 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jai | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.Select the CIty | Chennai | The entered data should be displayed in the "city" field | The entered data is displayed in the "city" field | pass
|  |  |  | 9.Enter the Recovery mail in the "Recovery email" field | jai@gmail.com | The entered data should be displayed in the"Recovery mail" field | The entered data is displayed in the"Recovery mail" field | pass
TC_012 | To validate RediffMail Account creation functionality with field level validation of " checkbox" field | 12 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jai | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.Select the CIty | Chennai | The entered data should be displayed in the "city" field | The entered data is displayed in the "city" field | pass
|  |  |  | 9.Enter the Recovery mail in the "Recovery email" field | man@gmail.com | The entered data should be displayed in the "Recovery mail" field | The entered data is displayed in the "Recovery mail" field | pass
|  |  |  | 10.select the "check box" |  | The "Recovery mail must disappear and the Select the Security Question and Enter an Answer and Mother's Maiden Name field" should be displayed | The "Recovery mail must disappear and the Select the Security Question and Enter an Answer and Mother's Maiden Name field" is displayed | pass
|  |  |  | 11.Select the Question from "Select the Security Question" dropdown field |  | All the four Questions must be displayed in the "Select the Security Question" dropdown field | All the four Questions must be displayed in the "Select the Security Question" dropdown field | pass
|  |  |  | 12.Enter some answer in the "Enter an Answer" field | biriyani | The entered data should be displayed in the "Enter an Answer" field | The entered data is displayed in the "Enter an Answer" field | pass
|  |  |  | 13.Enter the mother maiden name in the "Mother's Maiden name" field | parvathi | The entered data should be displayed in the "Mother's Maiden Name" field | The entered data is displayed in the "Mother's Maiden Name" field | pass
TC-013 | To validate RediffMail Account Creation Functionality with the field level validation of "Mobile Number" field | 13 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jay | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.Select the CIty | Chennai | The entered data should be displayed in the "city" field | The entered data is displayed in the "city" field | pass
|  |  |  | 9.Enter the Recovery mail in the "Recovery email" field | man@gmail.com | The entered data should be displayed in the "Recovery mail" field | The entered data is displayed in the "Recovery mail" field | pass
|  |  |  | 10.select the "check box" |  | The blue color tick should de displayed in the "check box" field | The blue color tick should de displayed in the "check box" field | pass
|  |  |  | 11.Enter the mobile in the "Mobile Number'' field | 7010516617 | The entered data should be displayed in the "Mother's Maiden Name" field | The entered data is displayed in the "Mother's Maiden Name" field | pass
TC_014 | To validate RediffMail Account Creation Functionality with the field level validation of "Captcha" field | 14 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jai | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.Select the CIty | Chennai | The entered data should be displayed in the "city" field | The entered data is displayed in the "city" field | pass
|  |  |  | 9.Enter the Recovery mail in the "Recovery email" field | man@gmail.com | The entered data should be displayed in the "Recovery mail" field | The entered data is displayed in the "Recovery mail" field | pass
|  |  |  | 10.select the "check box" |  | The blue color tick should de displayed in the "check box" field | The blue color tick should de displayed in the "check box" field | pass
|  |  |  | 11.Enter the mobile in the "Mobile Number'' field | 7010516617 | The entered data should be displayed in the"Monile Number" field | The entered data is displayed in the"Monile Number" field | pass
|  |  |  | 12.Enter the captcha in the "Captcha " field | NA | The entered data should be displayed in the " Captcha" field | The entered data is displayed in the " Captcha" field | pass
TC-015 | To validate RediffMail Account Creation Functionality with the field level validation of "Create My Account" field | 15 | Launch browser with url"www.Reddifmail.com"and navigate to account creation page | 1.Enter the full name in the " Full name" field | M Jayachandran | The entered data should be displayed in the "Full name" field | The entered data is displayed in the "Full name" field | pass
|  |  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | jai20 | The entered data should be displayed in the "RediffMail ID" field | The entered data is displayed in the "RediffMail ID" field | pass
|  |  |  | 3.Enter the password in the "Password" field | jai | The entered data should be displayed in the "Password" field | The entered data is displayed in the "Password" field | pass
|  |  |  | 4.Enter the password in the "Retype Password" field | jay | The entered data should be displayed in the "Retype Password" field | The entered data is displayed in the "Retype Password" field | pass
|  |  |  | 5.Select date of birth | 20/05/2004 | The entered data should be displayed in the " date of birth" field | The entered data is displayed in the " date of birth" field | pass
|  |  |  | 6.Select Gender | Male | The entered data should be displayed in the "Gender" field | The entered data is displayed in the "Gender" field | pass
|  |  |  | 7.Select the country | India | The entered data should be displayed in the "I Live in" field | The entered data is displayed in the "I Live in" field | pass
|  |  |  | 8.Select the CIty | Chennai | The entered data should be displayed in the "city" field | The entered data is displayed in the "city" field | pass
|  |  |  | 9.Enter the Recovery mail in the "Recovery email" field | man@gmail.com | The entered data should be displayed in the "Recovery mail" field | The entered data is displayed in the "Recovery mail" field | pass
|  |  |  | 10.select the "check box" |  | The blue color tick should de displayed in the "check box" field | The blue color tick should de displayed in the "check box" field | pass
|  |  |  | 11.Enter the mobile in the "Mobile Number'' field | 7010516617 | The entered data should be displayed in the "Mother's Maiden Name" field | The entered data is displayed in the "Mother's Maiden Name" field | pass
|  |  |  | 12.Enter the captcha in the "Captcha " field | NA | The entered data should be displayed in the " Captcha" field | The entered data is displayed in the " Captcha" field | pass
|  |  |  | 13.Click on the "Create My Account" button | NA | The message "Account Created Successfully" should be displayed | The message "Account Created Successfully" is displayed | pass

## Defect Log
Defect Log
| Project Name: |  |  | Project Start Date:
Version Number:
Author Name:
Defect ID | Defect description | Reproducible | Steps to Reproduce | Test Data | Status | Priority | Severity | Reporter Name | Reported Date | Assigned To | ScreenShot
DEF_001 | The error message "The password field and the Retype password field must match" should be displayed |  | 1.Enter the full name in the " Full name" field | Pavan Kalyan L | New | Medium | Medium | Pavan Kalyan L
|  |  | 2.Enter the Rediffmail in the "RediffMail Id" field | pavankalyanl@rediffmail.com
|  |  | 3.Enter the password in the "Password" field | Kal13
|  |  | 4.Enter the password in the "Retype Password" field | Kal13
|  |  | 5.Select date of birth | 2025-05-13
|  |  | 6.Select Gender | Male
|  |  | 7.Select the country | India
|  |  | 8.Select the CIty | Chennai
|  |  | 9.Enter the Recovery mail in the "Recovery email" field | pavankalyanl1318@gmail.com
|  |  | 10.select the "check box" | NA
|  |  | 11.Enter the mobile in the "Mobile Number'' field | 9345362981
|  |  | 12.Enter the captcha in the "Captcha " field | NYBA
|  |  | 13.Click on the "Create My Account" button | NA
ERROR MESSAGE: The error message is The password field and the Retype password field must match" is displayed

## RTM
Requirement Tracebility Matrix
Project Name: |  |  | Project Start Date:
Version Number: |  |  | Project End Date:
Requirement ID | Test Scenario ID | Test Case ID | Status | Defect ID | Remarks
REQ_001 | TS_001 | TC_001 | Covered
REQ_002 | TS_001 | TC_002 | Covered
REQ_003 | TS_001 | TC_003 TC_004 TC_005 | Covered
REQ_004 | TS_001 | TC_006 TC_007 TC_008 TC_009 | Covered
REQ_005 | TS_001 | TC_010 TC_011 TC_012 TC_013 TC_014 | Covered
REQ_006 | TS_001 | TC_015 TC_016 TC_017 TC_018 TC_019 TC_020 TC_021 TC_022 TC_023 TC_024 TC_025 TC_026 TC_027 | Not Covered | DEF_001
REQ_007 | TS_001 | TC_028 TC_029 TC_030 TC_031 TC_032 TC_033 TC_034 | Covered
REQ_008 | TS_001 | TC_035 TC_036 TC_037 TC_038 TC_039 TC_040 | Covered
REQ_009 | TS_001 | TC_041 TC_042 TC_043 TC_044 TC_045 TC_046 TC_047 | Covered
REQ_010 | TS_001 | TC_048 TC_049 TC_050 TC_051 TC_052 TC_053 TC_054 TC_055 | Covered
REQ_011 | TS_001 | TC_056 TC_057 TC_058 TC_059 TC_060 TC_061 TC_062 TC_063 TC_064 | Covered
REQ_012 | TS_001 | TC_065 TC_066 TC_067 TC_068 TC_069 TC_070 TC_071 TC_072 TC_073 TC_074 TC_075 TC_076 TC_077 | Covered
REQ_013 | TS_001 | TC_078 TC_079 TC_080 TC_081 TC_082 TC_083 TC_084 TC_085 TC_086 TC_087 TC_088 | Covered
REQ_014 | TS_001 | TC_089 TC_090 TC_091 TC_092 TC_093 TC_094 TC_095 TC_096 TC_097 TC_098 TC_099 TC_100 | Covered
REQ_015 | TS_001 | TC_101 TC_102 TC_103 TC_104 TC_105 TC_106 TC_107 TC_108 TC_109 TC_110 TC_111 TC_112 TC_113 | Covered